## Slide 1: Project Barton Update Zilker IoT Open-Source
06.11.2024

## Slide 2: Introduction to Barton
Barton is the extracted IoT parts of the Zilker project
Well-defined, friendly APIs backed by its own release cycles and documentation
Currently deployed in Zilker on all XB6/XB7/XB8 and in progress on XB10/XER10
Provides local/edge device support for Zigbee, Thread, Matter, and others
Includes configuration, firmware management, and backup/restore for gateway swap
Handles the complexities of Matter certificates and Fabric management
Check/Discuss: Enabler or Differentiator?
Communications (AWS)
Automations
Home Security
Zilker
Device Service
Zigbee
Matter
Barton
Extract!
RDK-M Device
EntOS Device
OpenWRT Device
IoT Bridge

## Slide 3: Project Phases
Overview of Phases:
Phase 1: Extraction
Phase 2: Internal Availability
Phase 3: Open-Source Release
Extraction Complete
Internally Available
Open Source Available
Q2
Q4
EoY

## Slide 4: Phase 1 - Extraction from Zilker
Objective:
  Identify and extract core IoT components from Zilker into new repository.
Key Activities:
  Separating public and private sources.
  First pass at new API.
  Bridge new API into old (no impact to Zilker)
Timeline:
  Expected duration: 1 month, completion in June.
Milestones:
  Local code extraction.
  New API bridged in.
  New and existing integration tests passing.

## Slide 5: Phase 2 – Internal Availability to Comcast/Sky
Objective:
  Formal APIs completed and functionality usable internally.
Key Activities:
  Final pass at new API.
  Internal architectural cleanup.
  Robust automated functional test framework.
  Zilker updates to better consume new API.
Timeline:
  Expected duration: ~4 months.
Milestones:
  New API complete.
  Internal cleanup complete.
  Automated tests provide sufficient coverage

## Slide 6: Phase 3 – Open-Source Release
Objective:
  Release Barton as an open-source project to RDK-M and others.
Key Activities:
  Preparing processes for external interactions (PR handling, etc.).
  Engage and follow Comcast Open-Source processes/procedures.
  Establishing open-source community guidelines.
Timeline:
  Expected duration: 1 month.
Milestones:
  Codebase release.
  Community guidelines published.
  RDK-M enabled.

## Slide 7: Thank you!