## Slide 1
RDK 8 / APOLLO V2
Status Update
Date: March 31, 2026

## Slide 2: Proposed Task Assignment Model
Infosys to create generic feature requirement tickets
Ticket Review
2. Comcast picks up any feature already on Comcast product roadmap
3. Infosys picks up features required for Apollo v2 not covered under step 1 above
4. RDKM to address any gaps for the community MVP where Comcast / Infosys may have proprietary solutions
1. Is this feature a candidate for Joint Development? If yes, setup team and assign owner

## Slide 3: RDK8 : Spec Readiness
Specification | ETA | Owner | Status
Core RDK | 31-Mar | Zoltan | 
RDK8 Firebolt® API spec | 27-Feb | Firebolt Working Group | 
RDK8 Firebolt® Lifecycle API | 31-Dec | Firebolt Working Group | 
Bolt (DAC 2.0) ** | 31-Mar | Native Apps Working Group | 
HAL | 31-Dec | RDKM | 
At Risk
Not Started
On track
Legend
Off track!
** DAC 2.0 spec is divided into multiple categories. Firebolt Core DONE, Firebolt Graphics WIP, Firebolt Media WIP, Life Cycle DONE and Icrypto TBD
Completed
Completed
Completed
Completed
Completed
Completed

## Slide 4: RDK8 : Feature Readiness
Feature | ETA | Dependency | Owner | Status
App Manager (Including rdk-window-manager) | Q1 2026 3 7 April | Firebolt Spec | RKDM / Infosys | 
Bolt Packages (including RALF utils and RALF pack) | Q1 2026 | Completed | Comcast / RDKM | 
Application Bundles – DAC 2.0 Bundles for Native Apps with Launcher + Run time config + GPU Layer Support* | Q1 2026 | DAC 2.0 Spec | RDKM / Infosys | 
Firebolt Client Library | Q1 2026 | Firebolt Spec | Sky | 
Containerized Browser Runtime with Launcher* | Q1 2026 | Firebolt Spec | Comcast / RDKM | 
RDK Reference UI upgrades | Q1 2026 | App Managers | RDKM | 
Graphics upgrade – Vulkan Support | Q3 2025 | NA | Comcast / RDKM | 
Platform Upgrades (Primary device) | Q1 2026 3 15 April | DRM Keys | RDKM | 
Kernel Upgrade 6.1 Kernel | Q1 2026 | NA | RDKM | 
Quarterly Core RDK MW Release | Q1 2026 8 April | NA | Comcast / RDKM | 
Performance issues on Broadcom Graphics | TBD | Vendor, Graphics | Comcast / RDKM | 
Not Started
On track
Legend
At Risk
Off track!
Completed
On track
Completed
* Risks: Being tested for the first time
Completed
Completed
Completed
Completed
Completed
Completed
On track
Completed
Off track!

## Slide 5: Apollo v2: Status Dashboard
Dashboard link: https://wiki.rdkcentral.com/x/7xpZGw
Status | #
Definition in progress | 4
Definition Complete | 9
Ready For Work | 7
Work In Progress | 1
Partner | Tickets
Comcast | 5
Infosys | 6
RDKM | 0
Joint | 10
Pending | 0
Chart: 
| Comcast | Infosys | RDKM | Joint | Pending
Tickets | 5 | 6 | 0 | 10 | 0
Chart: Progress Report
Definition In Progress | 4
Definition Complete | 9
Ready For Work | 7
Work In Progress | 1

## Slide 6: Apollo v2: Plan & Status
Task | Tentative ETA | Owner | Status
Super Epic Creation | 16-Jan | Infosys | 
Feature Epic Creation | 31-Jan | Infosys | 
Epic Review | 13-Feb | All | 
Allocation of Work & Project Plan * | 27-Feb | All | 
Project Plan Tracking Starts ** | 10-Mar | RDKM | 
Project Tracking Dashboard *** | 15-Mar | RDKM | 
At Risk
Not Started
On track
Legend
Completed
RDKDEV-1159
Completed
Completed
Completed
*** Will start tracking per Project Plan
* 2 DAC tickets definition in progress
Off track!
** Need assignment of tickets to developers & commitment with delivery timelines
BEING REPLANNED

## Slide 7: Detailed Action Item Tracker: Open items from last meetings
# | Action | Owner | ETA | Status
1 | Assigning tickets to leads for the “definition completed epics.” | All | March - 14 | OPEN
2 | Publish the Firebolt Player Design and Reference implementation | Yuri/Steve G | March- 6 March - 20 | OPEN
3 | Persistent License for Webapps – Follow-up session with Webkit and OCDM teams | Ajith/Anil | March – 14 April - 15 | OPEN
4 | Persistent License for Webapps – Need to review patch shared by Ozgur RDKDEV-1197 | All | April - 14 | OPEN
5 | Native App Firebolt Connect Strategy - Schedule call to review the strategy and ensure alignment for ApolloV2 | Oscar/Ajith | March – 31 TBD | OPEN
6 | Plan for RIALTO hardening for Netflix certification | Ajith/Anil | March - 31 | OPEN
7 | Need a plan and ETA for Rialto updates for Cobalt2027 AVPK 6&7 as per ApolloV2 scope | Neetika | April - 14 | OPEN
8 | Proposal to create user stories and tasks for more granular progress tracking. | All | March – 31 April - 14 | OPEN
9 | Schedule follow-up workshops for AppManager, OCDM, Player, Network Diagnostics, and Resource Monitor. | Ajith | April - 15 | OPEN

## Slide 8: Detailed Action Item Tracker: Open items from last meetings
# | Action | Owner | ETA | Status
10 | Identify the Dev owners and create user stories or tasks linking them to respected Epics for All Epics | All | April - 14 | OPEN
11 | Identify Jira project where User stories or tasks will be created and ensure everyone has access | Ajith | April - 15 | OPEN
12 | Review patch shared by Ozgur here - RDKDEV-1197 | All | April - 21 | OPEN
13 | Vulkan Graphics performance issue on Broadcom 74116 | RDKM | April – 30 | OPEN

## Slide 9: Action Item Tracker: Closed after last meeting
# | Action | Owner | ETA | Status
1 | Open sourcing of Window Manager | Anil | March – 31 April 3 | Closed
2 | Open sourcing of Entservices-testframework | Ajith/Anil | April - 31 | Closed

## Slide 10: Thanks!

## Slide 11: Action Item Tracker: Closed after last meetings
# | Action | Owner | ETA | Status
1 | Open-sourcing RALF Pack and RALF Utils | Anil | March - 23 | Closed
2 | App-specific Spec Tiger teams in Firebolt 8.x WG | Oscar | March – 31 | Closed
3 | RDK Tooling | Premzek/RDKM | April - 15 | Closed
4 | Network diagnostic feature proposal | Farhan | March - 31 | Closed
5 | Lead for DAC SDK and tooling tickets | All | March - 20 | Closed

## Slide 12: Introduction
RDK8 feature set does not fulfill all Apollo v2 requirements; Another release must be planned to address Apollo v2 requirements
Gaps shall be ticketed and tracked
Tickets will be reviewed by LG, Infosys, Comcast & RDKM allocated appropriately
This status meeting series will track feature readiness against a plan

## Slide 13: Action Item Tracker: Open items from last meetings
# | Action | Owner | ETA | Status
1 | Analyze the proposal to name the RDK releases as RDK8 and RDK9 and come back with recommendations. | Glee | Mar-31 | OPEN

## Slide 14: RDK8 : Core RDK Specifications
Specification | Status | URL
Core RDK |  | Core RDK Component List
RDK8 Firebolt® API spec |  | Firebolt APIs, JSON RPC, Client Libraries
HAL |  | HAL APIs